## Slide 1
INTERNAL AUDIT REPORT
Accounts Receivable
2018
TYPE
Financial Audit
SCOPE
North America Retail Banking
OVERALL RESULT
Fair
OWNER
alaudit

## Slide 2
AUDIT OVERVIEW
Accounts Receivable — 2018
OVERALL RESULT
Fair
Status: Completed · Not Closed · Resource ID: 3420
DESCRIPTION
2018 Accounts Receivable Scheduled Audit — evaluating accounting policies, revenue recognition, buyer return rights, and implementation of prior audit recommendations.
SCHEDULE
SCHEDULED START
Oct 23, 2018
Actual: Sep 1, 2018
SCHEDULED END
Mar 14, 2019
Actual: Not recorded
ESTIMATED HOURS
400
Actual: Not recorded
AUDIT PERIOD
Feb 1 – Mar 30, 2019
Audit Year: 2018 · Type: Financial
AUDITABLE ENTITY
Accounts Receivable
Scope: North America Retail Banking
⚠ ATTENTION REQUIRED
Audit started earlier than scheduled (Sep 1 vs Oct 23). Status is Completed but the audit is not formally closed. No actual end date or actual hours have been recorded.

## Slide 3
AUDIT SECTIONS — 20 PHASES
Phase Status Overview
14
COMPLETED
3
IN PROGRESS
3
NOT STARTED
1
CHANGES REQUIRED
PREPARATION (11)
01-01 Send notification letter
Complete
01-02 Initial project discussion
Complete
01-03 Discuss budget
Complete
01-04 Review regulations & guidance
Complete
01-05 Review prior reports
Complete
01-06 Complete risk assessment
⚠ Review: Changes Required
01-07 Prepare process flow charts
Complete
01-08 Request preliminary data
Complete
01-09 Complete planning memo
Complete
01-10 Complete scope matrix
Complete
01-11 Hold Opening meeting
Not Started
FIELD WORK (3)
02-01 Test Trade AR Listing
In Progress
02-02 Determine Existence of Balance
In Progress
02-03 Establish Proper Cutoff
In Progress
REPORT (4)
03-01 Prepare Draft Report
Not Started
03-02 Review Draft Report
Not Started
03-03 Prepare Final Report
Not Started
03-04 Review Final Report
Not Started
QUALITY REVIEW (2)
04-01 Hold Exit Conference
Not Started
04-02 Close Audit
Not Started
Completed
In Progress
Not Started
Changes Required

## Slide 4
AUDIT FINDINGS — 3 TOTAL
All Findings Open
3
OPEN
2
REPORTABLE
1
HIGH PRIORITY
1
SIGNIFICANT IMPACT
HIGH
Inconsequential
FIND_0126 · Preparer: ivyaudit
Incorrect journal entries
Status:
Open
Reportable:
Yes
Mgmt Owner:
Not assigned
Recommendation:
Not recorded
MED
Significant
FIND_0124 · Preparer: georgeaudit
Cycle diagrams do not exist except at overview level for any AR processes
Recommendation: Cycle diagrams needed before end of upcoming quarter close
Status:
Open
Reportable:
Yes
Mgmt Response:
Agree, will create Action Plan
LOW
More Than Incons.
FIND_0097 · Preparer: georgeaudit
Training of new managers on issues from the last audit has not occurred
Recommendation: Management should provide a training plan and schedule
Status:
Open
Reportable:
No
Mgmt Owner:
processowner

## Slide 5
ISSUES — 2 TOTAL
Both Issues Open and Overdue
2
OPEN
2
OVERDUE
1
HIGH PRIORITY
2
EVAL IN PROGRESS
HIGH PRIORITY
Open
OVERDUE — Due Nov 30, 2018
ISS001 · Type: Control Activity Missing · Impact: Significant · Assignee: georgeaudit
Certification requirements lacking
RESOLUTION STATUS
Evaluation in Progress
OVERDUE BY
~6+ years
MEDIUM PRIORITY
Open
OVERDUE — Due Nov 7, 2014
ISS-NA-CB-ERM-003 · Type: Other · Impact: Inconsequential · Assignee: itdirector2
Implement company-wide project to enhance corporate governance
Complete revision of Policies, Rules and Procedures within the company
RESOLUTION STATUS
Evaluation in Progress
OVERDUE BY
~10+ years

## Slide 6
CONCLUSION & RECOMMENDED ACTIONS
Summary
20
TOTAL PHASES
3
FINDINGS OPEN
2
ISSUES OPEN
KEY OBSERVATIONS
CRITICAL
Both issues are overdue — ISS001 by 6+ years, ISS-NA-CB-ERM-003 by 10+ years. Immediate escalation required.
CRITICAL
FIND_0126 (Incorrect journal entries, High priority) has no management owner or recommendation recorded.
WARNING
Audit is marked Completed but all Report and Quality Review phases are Not Started. Formal closure is blocked.
WARNING
Risk assessment review (01-06) has Changes Required status — unresolved before progressing to report phases.
GOOD
10 of 11 preparation phases fully completed. FIND_0124 has management agreement to create an Action Plan.
OVERALL AUDIT RESULT
Fair
Status: Completed · Not Closed
RECOMMENDED ACTIONS
1.
Escalate both overdue issues and assign clear remediation owners and deadlines.
2.
Assign management owner and recommendation to FIND_0126 immediately.
3.
Resolve the risk assessment review (01-06) before starting report phases.
4.
Complete field work (02-01, 02-02, 02-03) and begin the report phase.
5.
Progress through Quality Review phases to achieve formal audit closure.